Project Design: Planning the Editing Journey

In this chapter, you learn about the steps to consider before creating a DSE and what to keep in mind when consulting with DSEs that appear unfinished or under construction. The chapter shows how to plan a DSE around research questions and introduces the concrete elements this type of project usually requires: schedule, data modelling and objects definition, interface design and user experiences, as well as general and specific project management tasks (DMP, funding).

Keywords

Keyword1: Born Digital

Keyword2: Curation-driven approach

Keyword3: Data Management Plan

Keyword4: Funding

Keyword5: Project Planning

Keyword6: Research-driven approach

Keyword7: Retro-Digitisation

Keyword8: Workflow

, ,

⚙️ Technologies - The International Image Interchange Format (IIIF) is the standard image format used to link to scanned images of text (manuscript or print) - Text encoding technologies (e.g. XML/TEI) are used to structure texts according to the data model defined by the editor. - Project management tools (e.g. Gantt charts, Kanban boards, issue-/bug-trackers) help with planning, task distribution and workflow monitoring

🏛️ Support from 3rd parties (infrastructure) - Text+ Consulting: provides comprehensive advice from a team of agents on all issues relating to text and language-based research data (including editions). Contact via Helpdesk or via open consultation hours (Research Rendezvous) (no registration needed) - Data Steward Units in your home university might offer further support which has to be known during project planning. - Libraries, archives, and museums for questions regarding the sources, digitisation and licenses.

FAIR/CARE The FAIR and CARE principles should be used as guidelines at several key stages: - Project planning: anticipate data reuse, accessibility and sustainability of the DSE. - Data modelling: take care of structuring data in standardised and interoperable formats. - Data management plan (DMP): keep them in mind while documenting how data will be stored and shared - Planning for publication and dissemination: ensure findability (metadata, persistent identifiers (PID), catalogues) and accessibility.

📋 Checklist - Define the scope and objectives of the DSE. - Identify the edited objects and their level of granularity. - Establish a data model aligned with the research goals and the editorial principles. - Plan the workflow, tasks, and timeline (milestones, phases). - Evaluate the resources available (time, team, expertise). - Identify relevant infrastructures and support services. - Prepare an initial Data Management Plan (DMP). - Consider FAIR/CARE principles and data reuse. - Clarify legal aspects (rights, licenses, access conditions). - Assess funding needs and opportunities.

- 3.1. Project Planning

Careful planning is essential for creating a DSE. This chapter introduces a practical workflow for the planning phase, showing how to define scope and priorities, set a realistic timeline, and,  identify the people and resources needed. It also highlights how to keep your plan adaptable as the project evolves.

Keywords

Keyword1: Adaptability

Keyword2: Collaborators

Keyword3: Schedule

Keyword4: Tasks

Keyword5: Workflow

, , , ,

From Idea to Publication and Beyond: The Lifecycle of a DSE

The flowchart below offers an overview of what the lifecycle of a DSE can look like [Figure ?5?]. It presents one possible way in which a DSE project may develop, from initial conception to publication and beyond. This is not a fixed or universal model: depending on the nature, scope, duration, and institutional context of a project, individual steps may vary in order or take different forms. The purpose of the illustration is to support you, whether you are planning a project, applying for funding, or trying to understand an existing edition, in gaining an understanding of the phases and decisions that may be involved in making a DSE.

When you explore online digital editions, it may become apparent that some features are still missing and that parts of the planned content are not yet available. Many editions are released while they are still work in progress. This is due to the fact that online editions often follow different publication schedules than projects that are planned as a print volume, and they may be required to make early results publicly visible in order to meet funders’ expectations.

The illustrative flowchart assigns each step to a specific conceptual phase, but long-term projects rarely follow a strictly linear path. Publication may occur in several releases, and workflows often need revision as conditions change, for instance when new technologies (including AI) or infrastructure services become (un)available. It is important to check diligently how they can  be integrated into the workflow, taking into account what risks these technologies might bring to the process. Modular workflows, in which individual steps or tools can be replaced by functionally equivalent solutions, can help maintain a stable process while remaining open to adjustments.

Figure ?5? PLACEHOLDER FOR THE DSE LIFE FLOWCHART ILLUSTRATION

The Timeline of the DSE Project

One of the first planning outputs of a DSE project is a clear and realistic timeline. It links editorial decisions, like scope, depth and intended outputs, to workload, roles, and duration. In practice, a realistic timeline can only be established once the scope and depth of the edition have been defined. During planning, the main tasks are identified, iteration is anticipated assome steps overlap and may repeat, and tasks are translated into a small number of milestones. These milestones make the plan easier to communicate  and more usable for steering and reporting (➚ 3.1.3. From Workflow to Milestone and Tasks).

Providing a schedule is required in many funding schemes and useful  for projects with teams.  A schedule can also be a learning tool: it supports progress monitoring, the documentation of decisions , and the revision of estimates over time. Estimating the necessary resources, like time and staff, for each step can be difficult; here, it can be helpful to rely on concrete information, for instance by testing a work-flow on a data sample.

When estimating time and resources, the main elements to take into consideration often are :

- source acquisition and access conditions (including rights and licensing);

- digitisation and image quality control;

- transcription (manual or automatic text recognition (ATR) and its correction and validation);

- encoding/annotation and the creation of metadata;

- designing and deployment of the interface and long-term maintenance and preservation.

For the concrete implementation steps and the necessary tools, see ➚ 4. Implementation, and for team roles, partnerships, and support infrastructures, see ➚ 2.2. Surround yourself with the right people.

Timelines benefit from planned revision. When deviations occur, recording what caused them willimprove future estimates and helps to communicate changes to the team, to stakeholders and funders.

From Workflow to Milestones and Tasks

Turning a workflow into a workable plan generally involves moving from a workflow description to concrete tasks with responsibilities, and then to a schedule with milestones. The example below focusses on the planning level;detailed implementation steps are discussed in ➚ 4. Implementation.

Workflow → Tasks → Calendar

- The workflow is drafted by identifying what must happen to get from the sources to the public release, and, for long-term projects, to go over into the maintenance phase.

- The workflow is broken down into tasks by specifying responsibilities, inputs and outputs, and completion criteria (“done”).

- Tasks are grouped into milestones that can be communicated and tracked over time.

Suggested Milestones

- Corpus secured: sources identified, access conditions clarified (➚ 2.2.3. Rights and Licenses).

- Scope locked: priorities, minimum deliverables, and success criteria documented.

- Pilot completed: sample digitisation / transcription / encoding tested; estimates revised ( ➚4.1. From primary sources to digital data).

- Tools and working environment: selected and customised after evaluation (e.g. frameworks for XML editors to facilitate certain steps such as marking of lemmas, adding references to registries and so one; ➚ 4.1.2. Transcribing textual data, 4.1.3. Encoding textual data).

- Editorial and data model stable: guidelines, schema conventions, and QA approach agreed.

- Core dataset produced: planned coverage reached for transcription / encoding / metadata.

- Release ready: documentation, citation guidance, and dissemination plan prepared.

- Sustainability arranged: repository deposit and maintenance responsibilities confirmed (➚2.2.2. Institutions; ➚ 5.1. Facilitating maintenance).

Defining and Structuring the Data

This section explains how to define and structure the data of a DSE, which is a step in the project process called data modelling. It shows how to identify what you are editing (the “objects”), how detailed or granular your description should be, and how these choices shape both your edition and its possible uses.

Keywords

Keyword1: Authority files

Keyword2: Data modelling

Keyword3: Text Encoding

Keyword4: Interoperability

Keyword5: Standards

Keyword6: Granularity

What is Data Modelling?

At the beginning of a project, editors typically have a set of aims and beliefs of what they want to achieve with their edition. . These aims and beliefs may evolve over time or change, and this is not a problem, as long as they are clearly stated and soundly reasoned.Editors might want to achieve such things as publishing a readable text of a historical source, or providing materials and tools for data mining or computational text analysis, or contributing material to an already existing digital collection. When we model data, wetranslate these aims and beliefs into decisions about what is represented and how we structure our data. The concrete technical steps of how to implement these decisions are discussed in ➚4.2. The many lives of the data.

Projects that involve advanced tasks—such as refining a model, writing complex scripts, or performing lemmatisation (particularly for ancient or poorly documented languages)—tend to increase workload significantly. Ambitions therefore need to be adjusted: the focus should remain on what can realistically be achieved given the team’s time, skills, and disciplinary background, rather than on what could be done with unlimited resources.

Besides, it is always possible to modularise your work and add further layers at a later stage. However, your priority should be to produce a solid and consistent textual and data foundation on which further work can build. A well-designed data model can be easily simplified if necessary and extended later if more time or resources become available. In practice, it is often advisable to work in stages rather than aiming to publish a completely ‘encoded’ corpus at once.

Modelling and Implementation

Data modelling and implementation walk hand in hand, but they should be distinguished. Data modelling defines what you want to represent and how the data should be structured; implementation covers the concrete steps that turn this model into an operational edition (digitisation, transcription, encoding, publication, etc.; ➚ 4. Implementation). For example, if you want to create a critical digital edition and publish it on a web page:

- You have to choose an encoding schema adapted to your edition: structure and hierarchy of the text, lemmas, readings varying between witnesses, named entities, etc. → That is modelling.

- You must encode the data and make it accessible (e.g. by displaying the XML files in a web interface) → That is implementation.

Defining Edited Objects

Planning also requires defining the basic objects that will structure the data. In digital environments, texts are not only read as continuous documents, but also processed as structured data that must be identified and organised. A central planning question is therefore: what are the main objects of the edition, and how detailed should their description be?

Two main aspects can guide these decisions (and can be reflected in project design or in a funding application):

1. What kind of edition is being produced? Will it reproduce the layout of the source (topological/diplomatic edition), or follow a more interpretative or genetic approach? (➚ 1.2.3. Typology of DSE).

2. What is being edited? Which objects are included? Depending on the project, the edition may include various types of objects: texts preserved in manuscripts, inscriptions, papyri, fragments, individual documents (letters, emails), or other media such as audio or video. These objects often form hierarchical relationships. For example, a manuscript may contain several texts, while a single text may exist in multiple manuscripts. Identifying these relationships is a crucial step in structuring the data.

Granularity and Structure

Once the main objects are defined, the next step is to determine how detailed the structuring should be: this is granularity. Granularity involves identifying the entities an edition will contain and how they relate to each other. It may include:

- the edited object(s) and textual units;

- structure (e.g. chapters, sections, lines) and editorial layers (e.g. commentary, variants);

- entities and identifiers (persons, places, works, organisations; authority files orlinks).

The level of granularity should reflect the goals of the project. Defining it early on helps to anticipate what will be displayed and preserved in the final edition.

Digital editions often publish texts, but they generally consist of data beyond text as well. A DSE may include links to authority files, archival collections, or other external resources. Data models therefore benefit from designs that:

1. support your research questions and intended forms of presentation (e.g. linking texts and images, enabling navigation within and across resources)

2. guarante the long-term reusability of your data (e.g. interoperability, reuse in other projects, addition of new layers such as annotations)

Data modelling and presentation are distinct steps, but they are closely connected: the structure of your data must take into account how it will be displayed. For example, if you want to align a transcription precisely with manuscript lines, this relationship must be encoded in your data model.

At the data modelling stage, it is important to consider field standards, for example for text encoding (consult the guidelines of the Text Encoding Initiative – TEI) and for linking data with other digital resources (which authority files are appropriate? ➚ 4.2.2. The images and ➚ 4.2.3. The textual documents).

Finally, editorial guidelines need to be reflected in the data model, which requires clarification: how should the source documents be edited?

A few examples:

- Will you reproduce corrections or provide a final text version?

- What kind of data will you produce? Text files, introductory commentaries, annotations, registries with references to the persons, institutions, places, works (= entities), etc. mentioned the texts?

- How are the different data types connected with each other? Are they linked in the edition?

- How shall the edition be linked with other digital resources (e.g. search engines, biographical handbooks, encyclopedias, archival catalogues etc.) and how can it be achieved by the data model?

Your data modelling choices must be made carefully and should be well documented: documenting how and why data is structured the way it is will allow others to understand the process, reuse the data, and even build upon what has been done to enrich it or create something new on this basis.

Navigating the Edition: Defining the Interface

Planning the interface of a DSE means planning the user experience: who the users are, what they want to do, and how the edition helps them get there. Even when the underlying data are complex, navigation should make the edition understandable, explorable, and accessible to audiences.

Keywords:

Keyword1: Interface

Keyword2: Usability

Keyword3: User Experience

Audience and Use

Most readers will discover an edition through a web interface rather than through the underlying edited files. Interface planning therefore starts with clarifying intended audiences and use cases, and then deciding which features are essential and which are optional. “Intended audiences” and “use cases” are always a construct that has to be specified. It’s important to have a clear vision of the use(r) and to specify in which way your DSE can be a starting point for new research. These decisions are not purely scholarly, as they also impact workload, required expertise, and budget. A simple, robust interface may be the best choice for some projects, while others require multiple views (e.g., facsimile + transcription + variants) or additional exploration features. Priority is often given to what is necessary for the project’s goals, while “nice-to-have” features can be treated as modular extensions.

One has to be aware that an Open Source resource that complies by Open Science standards such as the FAIR principles is easy to reach and therefore great opportunity compared for instance to purely scholarly books. But it comes with challenges in terms of accessibility. Despite all the interoperability and machine readability it is essential to take into account, that they aim to be used by human beings in the first place. For technical implementation choices (frameworks, databases, deployment), see ➚ 4.2.4. Deployment and visualisation.

In a DSE, the interface is the intermediary between the structured data and human users. That means that an edition shows which research questions and user scenaries were anticipated by the editorial team while planning the DSE, e.g.; Who is this edition for, and what should they be able to do? The answers shape the information architecture (navigation, menus, landing pages, search), the level of explanation, and the balance between reading and exploration.

Typical audiences include the following users and scenarios:

- researchers and editors (citation, variants, provenance, advanced search, further philological, linguistic or historical analysis)

- students and teachers (guided reading, context, linguistic and realia commentary, stable references);

- non-academic audiences (discoverability, plain language, visual entry points);

- developers and data reusers (download options, documentation, Application Programming Interfaces (API) where relevant).

When an edition aims to reach learners (e.g., schools), involving educators early can be beneficial; the Darwin Correspondence Project is one example of an edition with strong teaching-oriented materials. Design decisions can also be grounded in actual practices through light-weight user research (short interviews, task-based tests, real scenarios); for instance, the Digitale Historisch-kritische Gesamtausgabe der Werke und Briefe von Jeremias Gotthelf explicitly follows human-centred design principles in order to reach a broad audience on the one hand and to translate the requirements of historical critical editing into the digital medium.

Conceptual Interface Choices

At the planning stage, interface design benefits from focusing on decisions that shape the user experience independently from any specific platform. One practical approach is to define a “minimum viable interface” (what users should be able to do in the first release of the DSE) and to treat additional features as optional, modular enhancements. Key choices include which core views will be provided—such as facsimiles, transcriptions, a reading text, variants, or commentary—and how these views relate to different audiences and uses (reading, teaching, exploration, or data reuse). Another early decision concerns the navigation model, for example browsing via collections and indices versus a search-first approach, as well as support for deep linking and stable citation. Transparency is equally important: As a user (or reader) of a DSE, you should be able to find the editorial principles, information about data provenance, and documentation about the technical aspects of the edition without effort. Planning for reuse also requires clarity about what can be downloaded, in which formats data are available, and under which licences they can be used (➚ 2.3.2. Rights and Licences).

Finally, sustainability considerations address how and for how long the interface and data will remain available and be maintained or preserved.  (➚ 5. Facilitating maintenance). For digital projects, the question of long-term preservation is an ongoing discussion. Maintenance, including necessary updates of software and applications, but also adjusting to changing modes of interaction with the digital product, is a question of budget, expertise, and institutional commitment. Some argue that a hybrid solution, i.e. an edition that is both digital and analogue, is a sensible compromise to ensure longevity and to make future costs more predicatable, while others point out that a truly digital edition cannot be reproduced in an analogue medium without losing a significant part, even though the data remains accessible and some presentation layers are reproducible. (Sahle, XXXX, p. X)

However, the decisions made regarding the audience on the one hand and the available funds on the other hand, also influence the way of developing the user interface. You could stick more or less to an existing user interface, that is offered by a publishing system/Content Management System or an institutional player. They can be adjusted, too, but within some limits. If you want to create a website from scratch, you will have to decide who you will to commission and how far you want to respect the users' needs and interests. If they shall be identified by user research, that has to be calculated (financially and in terms of time). To increase the usability it is wise to expand your team (at least temporarily) with web-design experts.

Platform or framework choices and technical implementation are found in ➚ 4.2.4. Deployment and visualisation.
Dissemination and reaching audiences are discussed in ➚ 5.2. Let people know about your edition.

User Accessibility and Usability

Accessibility is part of planning, not a finishing touch. It increases reach and usability for readers with disabilities, users on mobile devices (this requires a responsible design), and users with limited bandwidth. Where possible, accessibility checks and user feedback can be integrated early and repeated over time. Key aspects include:

- Clarity, with descriptive labels, consistent menus, and a homepage that explains how to use the edition.

- Perceivability: use sufficient contrast; do not only rely on colour to convey meaning; choose readable fonts and page layout.

- Operability, thanks to keyboard navigation and predictable focus behaviour, avoiding interaction that requires precise mouse actions.

- Alternatives: always put text alternatives for non-text content and captions or transcripts when and where relevant.

- Performance: be careful to create pages that load on slow connections or images served in appropriate sizes.

- Language: consider at least an English navigation layer if you target an international audience.

Structuring and Sustaining the Project

This section shows how documentation supports the planning and long-term sustainability of a DSE. It introduces the data management plan (DMP) as a practical, evolving instrument that connects timeline, data decisions, infrastructure, and responsible sharing in line with FAIR and CARE principles. It also outlines how funding applications influence scope, resources, and project modularity.

Keywords

Keyword1: Data Management Plan (DMP)

Keyword2: Documentation

Keyword3: Funding

Keyword 4: Sustainability

Why Documentation is Part of Planning

A DSE is defined not only by its scholarly content and technical design, but also by how it is organised, documented, and sustained over time. Documentation is therefore part of planning: it links the timeline and milestones (➚ 3.1. Project planning), data decisions (➚ 3.2. What are your objects), and team roles and institutional support (➚ 2.2. Surround yourself with the right people). At the planning stage, documentation typically covers the resources and services the project relies on, how project data is managed, and how it can be made findable and reusable (for example by following principles such as FAIR and CARE; ➚ 2.3. Research ethics and rights). It also clarifies how the work is supported institutionally and, when relevant, financially. In this context, the Open Science principles (Open Access, Open Source) provide a useful orientation; publishing data and results under licences that enable reuse and relying on open standards and tools, can improve transparency and long-term independence (➚ 2.3.1 The FAIR principles and why they matter).

The next sections focus on two practical planning instruments: the Data Management Plan (DMP) and the funding application.

The Data Management Plan

A data management plan (DMP) is a document that describes how project data will be collected, organised, documented, stored, shared, and preserved over time. While it is often required in funding applications, it should not be understood as a purely administrative exercise. For a DSE, it can function as a practical planning instrument that supports project structuring from the outset. In concrete terms, the DMP consolidates key planning decisions made so far. This includes both primary materials (texts, images, metadata) and data generated through the work (transcriptions, annotations, structured datasets, indices, etc.). It also addresses file formats, encoding and metadata standards, and documentation so that data remain understandable and reusable beyond initial publication (for concrete steps involved in producing a DSE, ➚ 4. Implementation). Writing a DMP early also helps identify infrastructures and services that can support the work throughout the data lifecycle.

A DMP typically addresses the practical questions that were discussed above, but organised and unified in a tracking document:

- What data will be used, produced or reused in the project?

- In which formats will the data be stored and shared?

- Which standards will be followed (e.g. TEI for text encoding, authority files for entities)?

- How will the data be documented (metadata, guidelines, documentation of choices)?

- Where will the data be stored during the project, and how will it be preserved in the long term?

- How and under which conditions will the data be shared or made accessible?

If the funding scheme requires a DMP, you need to answer these questions; keep in mind that you might have to change some aspects of your DMP during your editorial process. Make sure your funding scheme allows for later changes.

A DMP is an evolving document. It can and should be revised as the project develops, as new constraints appear, or as new opportunities arise. In this context, principles such as FAIR (Findable, Accessible, Interoperable, Reusable) and CARE (Collective Benefit, Authority to Control, Responsibility, Ethics) provide useful reference frameworks (➚ 2.3.1. The FAIR principles and why they matter). They help guide decisions to ensure that data can be discovered, accessed, and reused in a sustainable and responsible way.

The Application for Funding

Edition projects are often labour-intensive and time-consuming. They often rely on funding to pay the project team’s salaries and the purchase of licenses or subscriptions for software and applications.  For edition projects which are developed alongside research and teaching obligations, the timeline has to be extended considerably.  Funding is competitive, so early cost estimation (e.g., digitisation, licences, staff time, and possibly hosting/maintenance) and eligibility checks are important. In any case, contacting institutional research support units and consulting with the funding agency can be helpful before submission.

Early on in the planning phase, you need to decide how much funding is needed and which funding schemes fit your project best.  Many universities have units that support grant writing . In addition, Digital Humanities centres, libraries, or DSE related research groups may provide domain expertise and might become partners in a joint application. Partner coordination usually requires additional lead time.

To develop realistic expectations about budgets and sponsors, it can help to review comparable projects and the funders they acknowledge (see the DSE catalogues in ➚ 7. Appendix). This can also help identifying infrastructures that may be reused. For larger, multi-year projects, planning in modules can increase feasibility and funding success. Module one is often defined to deliver the foundations and a publishable result, followed by modules that build on it; for editions that publish several texts or works, each module can target a specific group of texts, media or collections  and/or the development and progressive embedding of consultation features.

For funding opportunities and support programmes ➚ 7. Appendix.

Bibliography

Editions cited in this chapter

Darwin Correspondence Project

Digitale Historisch-kritische Gesamtausgabe der Werke und Briefe von Jeremias Gotthelf

Resources and Literature

Bleier, Roman, Martina Bürgermeister, Helmut W. Klug, Frederike Neuber, and Gerlinde Schneider, eds. Digital Scholarly Editions as Interfaces. Schriften Des Instituts für Dokumentologie und Editorik 12. BoD, 2018.

Burnard, Lou. “On the Hermeneutic Implications of Text Encoding.” In New Media and the Humanities : Research and Applications : Proceedings of the First Seminar, “Computers, Literature and Philology”, Edinburgh, 7-9 September 1998, edited by Domenico Fiormonte and Jonathan Usher. Humanities Computing Unit, University of Oxford, 2001.

Chun, Wendy Hui Kyong, Richard Grusin, Patrick Jagoda, and Rita Raley. “The Dark Side of the Digital Humanities.” In Debates in the Digital Humanities 2016, edited by Matthew K. Gold and Lauren F. Klein. University of Minnesota Press, 2016. JSTOR. https://doi.org/10.5749/j.ctt1cn6thb.41.

Henzel, Katrin. “Digitale Genetische Editionen Aus Der Nutzerperspektive.” In Textgenese in Der Digitalen Edition, edited by Anke Bosse and Walter Fanta. De Gruyter, 2019. https://doi.org/10.1515/9783110575996-005.

International Research Office of the University of Padua. “Fair Data Management Plan. Guidelines and Annotated Template. Based on the Horizon Europe Data Management Plan Template.” September 18, 2024. https://biblio.unipd.it/biblioteca-digitale/per-chi-pubblica/documenti-e-materiali/unipd_dmp-guidelines_18-09-2024_v4-3.pdf.

Lange, Judith. “Einmal Alles, Bitte!” Chancen Und Herausforderungen Hybrider Editionen, editio, vol. 39, no. 1 (2025): 18–33. https://doi.org/10.1515/editio-2025-0002.

Sahle, Patrick. Digitale Editionsformen, Zum Umgang Mit Der Überlieferung Unter Den Bedingungen Des Medienwandels, 3 Bände. 2019 https://www.i-d-e.de/publikationen/schriften/s7-9-digitale-editionsformen/.

Schonhardt, Michael. “Do One Thing and Do It Well. Vier Prinzipien einer digitalen Editionspraxis im Spannungsfeld zwischen fachlichen Standards und Deep Learning.” Digitales Edieren gestern, heute und morgen Sonderband 7 (2025). https://doi.org/10.17175/SB007_005.

Smithies, James. “The Dark Side of DH.” In The Bloomsbury Handbook to the Digital Humanities, edited by James O’Sullivan. Digital Humanities. Bloomsbury Academic, 2023.

Van Mierlo, Wim. Scholarly Editing in Perspective. 1st ed. Cambridge University Press, 2025. https://doi.org/10.1017/9781009183772.

Zimmermann von, Christian. “Textphilologie – Kommentar – Usability. Eine Philologische Bilanz zum Übergang von der Buchedition zur Digitalen Edition.” Archiv Für Das Studium Der Neueren Sprachen Und Literaturen 262, no. 1 (2025): 1–25.